## Phases
PHASES | DETAILS |  | WHO
Phase 1: (by May, 2021)
Collect Data Base | Entities |  | Ibraheem
| Account: Unique ID, First name, Last name, email, Profile Description, Key word ID, Location ID, Nickname: A123456, Language ID |  | Ibraheem
| Location: Unique ID, G-location, city name, country name |  | Ibraheem
| Key words: Unique ID, title |  | Ibraheem
| Language: Unique ID, Name |  | Ibraheem
Webserver | Get |  | Ibraheem
| Post |  | Ibraheem
| Delete |  | Ibraheem
| patch |  | Ibraheem
Application Design | Splash screen | 1 | Tarek
| Login screen: login (password, Nickname), logo, create account, information text, | 2 | Tarek
| Create Account page: first name, last name, password, key words, location, language, profile description | 3 | Tarek
| Search page: Account, search bar, filter account key words, filter location, | 4 | Tarek
| Account page: Nickname, profile description (50 words), key words (up to 10), location (on/off)(list), Language, Search page button | 5a | Tarek
| Result page: Other Users (Nickname, 2 keywords +) | 5b | Tarek
| Other User account: Nickname, key words, location (if on), languages, profile description, request button (pops up with message) |  | Tarek
| Chat page: Nicknames Chat, Other user account button, Account page button, search page button, search page button |  | Tarek
Phase 2:
| Blocked Accounts: Unique ID, Blocked Account ID, Block By Account ID |  | Ibraheem
| Chat Table: Unique ID, Nickname 1, Nickname 2 |  | Ibraheem
| Chat Messages: Unique ID, Created at, Chat ID |  | Ibraheem
| Request Table: |  | Ibraheem
Phase 3:
Testing | Q&A
Edits and Updates
Phase 4:
Deploy Android
Marketing
Assessment of success
Deploy IOS

## Timetable
TIMETABLE
Phase 1
|  | Week 1 Jan 25-31 | Week 2 Feb 1-7 | Week 3 Feb 8-14 | Week 4 Feb 15-21 | Week 5 Feb 22-28 | Week 6 Mar 1-7 | Week 7 Mar 8-14 | Week 8 Mar 15-21 | Week 9 Mar 22-28 | Week 10 Mar 29-Apr 4 | Week 11 Apr 5-11 | Week 12 Apr 12-18 | Week 13 Apr 19-25 | Week 14 Apr 26-May 2 | Week 15 May 3-9
Collect Data Base
| Account | Data Base
| Location | Data Base
| Key words | Data Base
| Language | Data Base
Application Design
| Splash screen |  | App
| Login screen |  | App | App | Webserver
| Create Account page |  |  |  | App | App | Webserver | Webserver
| Search page | [6 empty] | App | App | Webserver
| Result page | [9 empty] | App | Webserver
| Account page | [11 empty] | App | App | Webserver | Webserver
| Other User account | [13 empty] | App | App
Chat page
[5 empty] | Friday Feb 21 Meeting |  |  |  |  | Friday Mar 28 Meeting
[5 empty] | Check progress |  |  |  |  | Assessment and future plan | [5 empty] | TAREK
IBRAHEEM